## Gantt
Biological Foundation Models — Research Project Plan
As of September 26, 2026. Fall weeks start Monday; January–March 2027 is an adjustable monthly horizon.
██ = scheduled work ◆ = milestone Conditional = candidate work, subject to scope and feasibility.
Dates are inclusive. Details lists expected outputs. |  |  |  |  | September 2026 |  |  |  | October 2026 |  |  |  | November 2026 |  |  |  |  | December 2026 |  |  |  | 2027
ID | Task / research outcome | Status | Start | End | 9/7 | 9/14 | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | Jan | Feb | Mar
Stage 1: understanding and reproducibility
1 | Initial six-paper review | Complete | Sep 7 | Sep 21 | bar: September 2026 9/7 to September 2026 9/21
2 | Continue paper synthesis and notebook walkthrough | In progress | Sep 21 | Oct 5 | bar: September 2026 9/21 to October 2026 10/5
3 | Check label meaning, sequence regions and duplicates | In progress | Sep 21 | Oct 4 | bar: September 2026 9/21 to September 2026 9/28
4 | Check train/test separation and preprocessing | In progress | Sep 21 | Oct 4 | bar: September 2026 9/21 to September 2026 9/28
5 | Trace runs, seeds and reproducibility evidence | In progress | Sep 21 | Oct 4 | bar: September 2026 9/21 to September 2026 9/28
6 | Interpret representation metrics and pilot findings | In progress | Sep 21 | Oct 4 | bar: September 2026 9/21 to September 2026 9/28
7 | Draft an operational definition of alignment | In progress | Sep 21 | Oct 4 | bar: September 2026 9/21 to September 2026 9/28
8 | Map BioLangFusion methods to our inputs | Planned | Sep 28 | Sep 30 | bar: September 2026 9/28
9 | Build and check a BioLangFusion methods pilot | Planned | Oct 1 | Oct 4 | bar: September 2026 9/28
10 | Draft Stage 1 methods and findings in Overleaf | In progress | Sep 26 | Oct 4 | bar: September 2026 9/21 to September 2026 9/28
11 | Clarify the lab tokenizer and benchmark opportunity | Planned | Sep 28 | Oct 5 | bar: September 2026 9/28 to October 2026 10/5
12 | Prepare the Oct 5 evidence and question set | Planned | Oct 1 | Oct 4 | bar: September 2026 9/28
13 | Oct 5 review and working alignment definition | Planned | Oct 5 | Oct 5 | bar: October 2026 10/5
14 | Revise Stage 1 claims, figures and methods | Planned | Oct 6 | Oct 11 | bar: October 2026 10/5
15 | Specify the first matched comparison protocol | Planned | Oct 6 | Oct 11 | bar: October 2026 10/5
Stage 2: experiments and interpretation
16 | Harden single-model and simple-fusion baselines | Planned | Oct 6 | Oct 11 | bar: October 2026 10/5
17 | Run matched BioLangFusion-style comparisons | Planned | Oct 12 | Oct 18 | bar: October 2026 10/12
18 | Repeat diagnostics and null/control comparisons | Planned | Oct 12 | Oct 18 | bar: October 2026 10/12
19 | Interpret baseline findings and revise the next experiment | Planned | Oct 19 | Oct 25 | bar: October 2026 10/19
20 | Prepare Coupled Mamba inputs and feasibility tests | Planned | Oct 12 | Oct 25 | bar: October 2026 10/12 to October 2026 10/19
21 | Evaluate Coupled Mamba against matched baselines | Planned | Oct 26 | Nov 8 | bar: October 2026 10/26 to November 2026 11/2
22 | Candidate layer and PCA/variance comparisons | Conditional | Oct 19 | Nov 1 | bar: October 2026 10/19 to October 2026 10/26
23 | Candidate alignment-objective ablation | Conditional | Nov 2 | Nov 8 | bar: November 2026 11/2
24 | Candidate additional RNA-encoder comparisons | Conditional | Nov 9 | Nov 15 | bar: November 2026 11/9
25 | Candidate IsoFormer-style fusion comparison | Conditional | Nov 9 | Nov 15 | bar: November 2026 11/9
26 | Agree tokenizer benchmark feasibility and protocol | Conditional | Oct 6 | Oct 18 | bar: October 2026 10/5 to October 2026 10/12
27 | Candidate lab-tokenizer benchmark pilot | Conditional | Nov 2 | Nov 15 | bar: November 2026 11/2 to November 2026 11/9
28 | Repeat runs, quantify uncertainty and revise claims | Planned | Oct 12 | Nov 22 | bar: October 2026 10/12 to November 2026 11/16
29 | Synthesize evidence, limitations and next decisions | Planned | Nov 16 | Nov 29 | bar: November 2026 11/16 to November 2026 11/23
Research writing and coordination
30 | Research coordination and decision review | In progress | Sep 14 | Mar 31 | [17 empty] | ██ | ██ | ██ | bar: September 2026 9/14 to December 2026 12/28
32 | Maintain and revise the living Overleaf manuscript | In progress | Sep 26 | Mar 31 | [17 empty] | ██ | ██ | ██ | bar: September 2026 9/21 to December 2026 12/28
CAP6942 course deliverables
33 | Bibliography, Research Canvas and project plan | In progress | Sep 26 | Sep 27 | bar: September 2026 9/21
34 | Prepare final course report, presentation and video | Planned | Nov 16 | Dec 6 | bar: November 2026 11/16 to November 2026 11/30
35 | Course rehearsal checkpoint | Planned | Dec 1 | Dec 1 | bar: November 2026 11/30
36 | Final course report checkpoint | Planned | Dec 7 | Dec 7 | bar: December 2026 12/7
37 | Course presentation and video checkpoint | Planned | Dec 8 | Dec 8 | bar: December 2026 12/7
Research continuation
38 | Further experiments and external validation | Conditional | Jan 4 | Feb 28 | [17 empty] | ██ | ██
39 | Consolidate manuscript and review publication readiness | Planned | Feb 1 | Mar 31 | [18 empty] | ██ | ██
40 | March research review and next-step decision | Planned | Mar 31 | Mar 31 | [19 empty] | ◆
Update the dates and corresponding week cells together. This workbook is a schedule snapshot; dates do not automatically move the bars.

## Details
Expected outputs and dependencies
IDs match the Gantt. Dependencies refer to the outputs needed before a later task can be completed.
ID | Task / research outcome | Expected output / review condition | Prerequisite IDs
Stage 1: understanding and reproducibility
1 | Initial six-paper review | Complete the initial six-paper review and retain paper notes for continued interpretation and discussion. | —
2 | Continue paper synthesis and notebook walkthrough | Explain biological inputs, frozen encoders, pooling, probes and metrics; connect each retained result to the relevant paper and its limitations. | —
3 | Check label meaning, sequence regions and duplicates | Record assay/target provenance, retained rows, sequence regions, duplicates and translation assumptions before drawing biological conclusions. | —
4 | Check train/test separation and preprocessing | Identify evaluation unit; check whether duplicate or related sequences cross train/test boundaries and whether fitted preprocessing uses training data only. Document what the split can support. | —
5 | Trace runs, seeds and reproducibility evidence | Link selected outputs to notebook, data, model revisions, environment, split and seed settings. Compare reruns and investigate differences in results. | —
6 | Interpret representation metrics and pilot findings | Explain what CKA, neighborhood, CCA/retrieval and predictive probes measure; distinguish observations from explanations. Prepare PCA/variance and layer-choice questions for Mina. | —
7 | Draft an operational definition of alignment | Define objects being related, biological correspondence versus representation similarity, sample/position unit, metric, reference or null, and permitted conclusions. Keep useful fusion as a separate test. | —
8 | Map BioLangFusion methods to our inputs | Compare paper and local checkpoints, tokenization, sequence regions, codon mapping, pooling, labels, splits and metrics. Document the changes needed to adapt the method to our inputs. | —
9 | Build and check a BioLangFusion methods pilot | Test input/feature correspondence and selected simple fusion methods in a small prototype. Compare outputs with controls and bring feasibility findings and deviations from the paper to the October 5 review. | 8
10 | Draft Stage 1 methods and findings in Overleaf | Join Mina’s project, draft Stage 1 background/methods, attach supported figures and annotate unresolved claims. This is the first writing increment of the living manuscript. | —
11 | Clarify the lab tokenizer and benchmark opportunity | Ask Julian for the exact group, tokenizer/paper and intended benchmark task. Establish inputs, access, comparison unit and collaborators before promising a shared experiment. | —
12 | Prepare the Oct 5 evidence and question set | Assemble the explainable pipeline, source-linked findings, unresolved results, BioLangFusion pilot status and alignment-definition proposal. Distinguish established evidence from open hypotheses. | —
13 | Oct 5 review and working alignment definition | Review evidence with Mina and agree a working definition of alignment, its measurements and limits, and the next comparison. Record remaining questions and required revisions. | 2, 3, 4, 5, 6, 7, 9, 10, 12
14 | Revise Stage 1 claims, figures and methods | Incorporate Mina’s feedback in the notebook explanations and manuscript; correct unsupported interpretations and identify specific reruns or experiments needed. | 13
15 | Specify the first matched comparison protocol | Set biological question, target, evaluation unit, data exclusions, checkpoints, preprocessing, metrics, seeds, tuning budget and success/stop criteria. Architecture priority remains Coupled Mamba; details follow the review. | 13
Stage 2: experiments and interpretation
16 | Harden single-model and simple-fusion baselines | Prepare comparable single-encoder and concatenation + MLP predictors, input tests and controlled configurations. Keep the original linear concatenation probe distinct. Final comparisons use protocol 15. | 13
17 | Run matched BioLangFusion-style comparisons | Compare selected paper-inspired fusion methods and unimodal baselines on the same evaluation data, with adaptations and resources reported. Preserve null or negative results. | 9, 15, 16
18 | Repeat diagnostics and null/control comparisons | Check label/feature controls, synonymous-input behavior and representation diagnostics under the agreed evaluation. Test whether the claimed signal survives the relevant nulls. | 14, 15, 16
19 | Interpret baseline findings and revise the next experiment | Compare effect sizes, variation and failure cases; distinguish geometry from predictive complementarity. Revise the question and manuscript before choosing additional complexity. | 17, 18
20 | Prepare Coupled Mamba inputs and feasibility tests | Implement the prioritized architecture with explicit sequence/feature correspondence; test dimensions, controlled cases and resource feasibility while baseline analysis proceeds. | 15, 16
21 | Evaluate Coupled Mamba against matched baselines | Compare predictive performance, uncertainty, runtime and memory under the matched evaluation protocol. Interpret gains, losses or unchanged performance against the baseline. | 19, 20
22 | Candidate layer and PCA/variance comparisons | After choosing the relevant encoder/layer question, compare selected representations or variance subspaces. Fit any reduction within training data and separate using an earlier layer from truncating or retraining a model. | 18
23 | Candidate alignment-objective ablation | If selected, compare the same fusion setup with and without the specified alignment objective under matched tuning. The pilot’s alignment/error association is not evidence that the loss must help or hurt. | 19, 20
24 | Candidate additional RNA-encoder comparisons | If selected, compare individual checkpoints and combinations while controlling downstream capacity, input coverage and tuning. Different pretraining corpora alone do not establish complementarity. | 19
25 | Candidate IsoFormer-style fusion comparison | Evaluate the second-priority cross-attention candidate only if the reviewed research question and resource budget justify it. Report relevant differences from IsoFormer’s fine-tuning regime. | 21
26 | Agree tokenizer benchmark feasibility and protocol | With the identified lab group, agree a shared task, data, tokenizer version, access and fair comparison protocol. | 11, 13
27 | Candidate lab-tokenizer benchmark pilot | Run only after collaborators agree scope and access and a matched protocol exists. Keep tokenizer effects separate from model capacity, training data and downstream evaluation differences. | 26
28 | Repeat runs, quantify uncertainty and revise claims | Repeat selected configurations as results arrive; investigate variation, leakage or contradictory findings, and revise claims. This spans the experiment cycle rather than following implementation as a single final check. | 15, 16
29 | Synthesize evidence, limitations and next decisions | Build a comparison table with sources/runs, uncertainty, resource costs, negative findings and scope limits. Review which conclusions are supported and which further experiments are justified. | 19, 21
Research writing and coordination
30 | Research coordination and decision review | Maintain the questions, decisions and follow-ups from regular team and advisor discussions. Confirm future meeting dates with Mina. | —
32 | Maintain and revise the living Overleaf manuscript | Update methods, figures, claims, citations and open questions as research changes. Writing begins with Stage 1 and continues through review, new experiments and later consolidation. | —
CAP6942 course deliverables
33 | Bibliography, Research Canvas and project plan | Submit the annotated bibliography and Research Canvas for Team Assignment 1, and the research project plan for Team Assignment 2. Both are due September 27 at 23:59 Eastern. | —
34 | Prepare final course report, presentation and video | Adapt the evolving manuscript and evidence to the course report, presentation and video requirements. Rehearse explanations and incorporate teammate and advisor feedback. | —
35 | Course rehearsal checkpoint | Rehearse the scientific account and record corrections; confirm the course’s exact instructions in WebCourses. | —
36 | Final course report checkpoint | Review evidence, attribution and AI disclosure; confirm and complete the required course submission. | 34, 35
37 | Course presentation and video checkpoint | Deliver the course presentation/video using the reviewed evidence and acknowledged limitations. | 34, 35
Research continuation
38 | Further experiments and external validation | Select and run extensions justified by the reviewed evidence, biological relevance, collaborators and available resources. | 29
39 | Consolidate manuscript and review publication readiness | Refine the manuscript already underway, integrate additional evidence and seek group feedback. Venue, submission date and final research end remain undecided. | —
40 | March research review and next-step decision | Review the evidence and decide whether to extend the experiments, revise the manuscript, prepare a submission or change direction. Adjust the timeline to the chosen next steps. | 39
Planning notes
Update the dates and corresponding week cells together in Gantt. Keep each task ID unchanged when editing its expected output or prerequisites.
The team completed the initial six-paper review by September 21. Continued interpretation and discussion run through the October 5 meeting. September 21 start dates for current work are approximate planning anchors.
October 5 is the review with Mina and the target for a working alignment definition. Stage 1 includes the immediate revisions after that meeting. Future experiment dates are proposed windows.
Coupled Mamba is the priority architecture comparison. Optional layer/PCA, alignment-loss, additional RNA-encoder and IsoFormer comparisons depend on earlier findings and available capacity. The tokenizer and collaborating group must first be identified with Julian.
The bibliography, Research Canvas and project plan are due September 27 at 23:59 Eastern. December 1, 7 and 8 checkpoints come from the course schedule; confirm the corresponding WebCourses deadlines.
AI supports implementation, paper discussion, analysis and writing throughout the project. Each research task includes interpreting its evidence and revising the resulting claims.
Coordination began September 14. Stage 1 manuscript drafting begins September 26 and continues in Overleaf as the work develops. March is a planning horizon rather than a fixed research endpoint.