## Slide 1
multimodal-bio-fusion | Research Project Plan
Weekly schedule for fall 2026, with a provisional continuation through March 2027
Task / research outcome
Status
9/7
9/14
9/21
9/28
10/5
10/12
10/19
10/26
11/2
11/9
11/16
11/23
11/30
12/7
12/14
12/21
12/28
Jan
Feb
Mar
Stage 1 | Understanding, reproducibility and alignment
Initial six-paper review
Complete
Paper discussion, data checks and interpretation
In progress
BioLangFusion/IsoFormer pilot with DNA
Planned
Oct 5 review and working alignment definition
Planned
Feedback revisions and comparison protocol
Planned
Stage 2 | Experiments and interpretation
Baseline and Coupled Mamba comparisons
Planned
Controls, repeated runs and interpretation
Planned
Optional model, layer and tokenizer comparisons
Conditional
Research writing and coordination
Team coordination and research decisions
In progress
Living Overleaf manuscript
In progress
CAP6942 | Course deliverables
Bibliography, Research Canvas and project plan | Sep 27
In progress
Prepare final report, presentation and video
Planned
Rehearsal | Dec 1
Planned
Final report | Dec 7
Planned
Presentation and video | Dec 8
Planned
Research continuation | Provisional January–March 2027
Further experiments and external validation
Conditional
Manuscript consolidation and March review
Planned
Complete
In progress
Planned
Conditional
Milestone / deadline
As of Sep 29, 2026
AI supports literature study, coding, analysis and writing. Review and interpretation are included in the scheduled work.
Columns show week starting dates, then months in 2027. Course dates follow the syllabus schedule. Research completion remains open.
1
Notes: Biological Foundation Models | Research Project Plan
The initial six-paper review was completed by September 21. Continued discussion and scientific interpretation remain active.
Dates beyond current work are planning windows. September 21 start dates for ongoing tasks are approximate anchors, not reconstructed activity logs.
October 5 is the next planned Mina meeting. The Stage 1 milestone is a working definition of alignment and a decision about the next matched comparison. Specify the objects being aligned, biological question, unit, metric and reference, and what the result can support.
Stage 1 includes early fusion prototyping to develop understanding. Stage 2 is the proposed structured comparison programme following the review. Feedback may change its scope and timing.
The Coupled Mamba priority follows the project README and the September 23 meeting. Optional comparisons are candidates, and the team will select a feasible subset.
Research coordination began September 14. Stage 1 manuscript drafting is underway in Overleaf and continues as methods and findings change.
The September 27 deadline covers the bibliography and Research Canvas assignment and the research project plan assignment. December 1, 7 and 8 course dates follow the Fall 2026 CAP6942 schedule; WebCourses controls any changes.
January–March is a provisional continuation window. The research end and publication submission date have not been set.
The lab tokenizer and collaborating group still need to be identified. Clarifying the opportunity precedes committing to a benchmark.
AI supports literature study, implementation, analysis and writing. Source checking, experiment interpretation and research decisions are included in each relevant work package.
AI assistance: OpenAI Codex assisted with organizing and wording this research plan. Dates and task descriptions were compared with the course schedule, project README and team meeting notes.
Stage 1 | Understanding, reproducibility and alignment
1. Initial six-paper review
2026-09-07 to 2026-09-21; Complete.
Expected outcome: Complete the initial six-paper review and retain paper notes for continued interpretation and discussion.
Prerequisites: None specified.
2. Continue paper synthesis and notebook walkthrough
2026-09-21 to 2026-10-05; In progress.
Expected outcome: Explain biological inputs, frozen encoders, pooling, probes and metrics; connect each retained result to the relevant paper and its limitations.
Prerequisites: None specified.
3. Check label meaning, sequence regions and duplicates
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Record assay/target provenance, retained rows, sequence regions, duplicates and translation assumptions before drawing biological conclusions.
Prerequisites: None specified.
4. Check train/test separation and preprocessing
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Identify evaluation unit; check whether duplicate or related sequences cross train/test boundaries and whether fitted preprocessing uses training data only. Document what the split can support.
Prerequisites: None specified.
5. Trace runs, seeds and reproducibility evidence
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Link selected outputs to notebook, data, model revisions, environment, split and seed settings. Compare reruns and investigate differences in results.
Prerequisites: None specified.
6. Interpret representation metrics and pilot findings
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Explain what CKA, neighborhood, CCA/retrieval and predictive probes measure; distinguish observations from explanations. Prepare PCA/variance and layer-choice questions for Mina.
Prerequisites: None specified.
7. Draft an operational definition of alignment
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Define objects being related, biological correspondence versus representation similarity, sample/position unit, metric, reference or null, and permitted conclusions. Keep useful fusion as a separate test.
Prerequisites: None specified.
8. Map BioLangFusion methods to our inputs
2026-09-28 to 2026-09-30; Planned.
Expected outcome: Compare paper and local checkpoints, tokenization, sequence regions, codon mapping, pooling, labels, splits and metrics. Document the changes needed to adapt the method to our inputs.
Prerequisites: None specified.
9. Build and check a BioLangFusion methods pilot
2026-10-01 to 2026-10-04; Planned.
Expected outcome: Test input/feature correspondence and selected simple fusion methods in a small prototype. Compare outputs with controls and bring feasibility findings and deviations from the paper to the October 5 review.
Prerequisites: 8.
13. Oct 5 review and working alignment definition
2026-10-05 to 2026-10-05; Planned.
Expected outcome: Review evidence with Mina and agree a working definition of alignment, its measurements and limits, and the next comparison. Record remaining questions and required revisions.
Prerequisites: 2, 3, 4, 5, 6, 7, 9, 10, 12.
14. Revise Stage 1 claims, figures and methods
2026-10-06 to 2026-10-11; Planned.
Expected outcome: Incorporate Mina’s feedback in the notebook explanations and manuscript; correct unsupported interpretations and identify specific reruns or experiments needed.
Prerequisites: 13.
15. Specify the first matched comparison protocol
2026-10-06 to 2026-10-11; Planned.
Expected outcome: Set biological question, target, evaluation unit, data exclusions, checkpoints, preprocessing, metrics, seeds, tuning budget and success/stop criteria. Architecture priority remains Coupled Mamba; details follow the review.
Prerequisites: 13.
Stage 2 | Experiments and interpretation
16. Harden single-model and simple-fusion baselines
2026-10-06 to 2026-10-11; Planned.
Expected outcome: Prepare comparable single-encoder and concatenation + MLP predictors, input tests and controlled configurations. Keep the original linear concatenation probe distinct. Final comparisons use protocol 15.
Prerequisites: 13.
17. Run matched BioLangFusion-style comparisons
2026-10-12 to 2026-10-18; Planned.
Expected outcome: Compare selected paper-inspired fusion methods and unimodal baselines on the same evaluation data, with adaptations and resources reported. Preserve null or negative results.
Prerequisites: 9, 15, 16.
20. Prepare Coupled Mamba inputs and feasibility tests
2026-10-12 to 2026-10-25; Planned.
Expected outcome: Implement the prioritized architecture with explicit sequence/feature correspondence; test dimensions, controlled cases and resource feasibility while baseline analysis proceeds.
Prerequisites: 15, 16.
21. Evaluate Coupled Mamba against matched baselines
2026-10-26 to 2026-11-08; Planned.
Expected outcome: Compare predictive performance, uncertainty, runtime and memory under the matched evaluation protocol. Interpret gains, losses or unchanged performance against the baseline.
Prerequisites: 19, 20.
18. Repeat diagnostics and null/control comparisons
2026-10-12 to 2026-10-18; Planned.
Expected outcome: Check label/feature controls, synonymous-input behavior and representation diagnostics under the agreed evaluation. Test whether the claimed signal survives the relevant nulls.
Prerequisites: 14, 15, 16.
19. Interpret baseline findings and revise the next experiment
2026-10-19 to 2026-10-25; Planned.
Expected outcome: Compare effect sizes, variation and failure cases; distinguish geometry from predictive complementarity. Revise the question and manuscript before choosing additional complexity.
Prerequisites: 17, 18.
28. Repeat runs, estimate uncertainty and revise interpretations
2026-10-12 to 2026-11-22; Planned.
Expected outcome: Repeat selected configurations as results arrive; investigate variation, leakage or contradictory findings, and revise claims. This spans the experiment cycle rather than following implementation as a single final check.
Prerequisites: 15, 16.
29. Synthesize evidence, limitations and next decisions
2026-11-16 to 2026-11-29; Planned.
Expected outcome: Build a comparison table with sources/runs, uncertainty, resource costs, negative findings and scope limits. Review which conclusions are supported and which further experiments are justified.
Prerequisites: 19, 21.
22. Candidate layer and PCA/variance comparisons
2026-10-19 to 2026-11-01; Conditional.
Expected outcome: After choosing the relevant encoder/layer question, compare selected representations or variance subspaces. Fit any reduction within training data and separate using an earlier layer from truncating or retraining a model.
Prerequisites: 18.
23. Candidate alignment-objective ablation
2026-11-02 to 2026-11-08; Conditional.
Expected outcome: If selected, compare the same fusion setup with and without the specified alignment objective under matched tuning. The pilot’s alignment/error association is not evidence that the loss must help or hurt.
Prerequisites: 19, 20.
24. Candidate additional RNA-encoder comparisons
2026-11-09 to 2026-11-15; Conditional.
Expected outcome: If selected, compare individual checkpoints and combinations while controlling downstream capacity, input coverage and tuning. Different pretraining corpora alone do not establish complementarity.
Prerequisites: 19.
25. Candidate IsoFormer-style fusion comparison
2026-11-09 to 2026-11-15; Conditional.
Expected outcome: Evaluate the second-priority cross-attention candidate only if the reviewed research question and resource budget justify it. Report relevant differences from IsoFormer’s fine-tuning regime.
Prerequisites: 21.
26. Agree tokenizer benchmark feasibility and protocol
2026-10-06 to 2026-10-18; Conditional.
Expected outcome: With the identified lab group, agree a shared task, data, tokenizer version, access and fair comparison protocol.
Prerequisites: 11, 13.
27. Candidate lab-tokenizer benchmark pilot
2026-11-02 to 2026-11-15; Conditional.
Expected outcome: Run only after collaborators agree scope and access and a matched protocol exists. Keep tokenizer effects separate from model capacity, training data and downstream evaluation differences.
Prerequisites: 26.
Research writing and coordination
30. Research coordination and decision review
2026-09-14 to 2027-03-31; In progress.
Expected outcome: Maintain the questions, decisions and follow-ups from regular team and advisor discussions. Confirm future meeting dates with Mina.
Prerequisites: None specified.
32. Maintain and revise the living Overleaf manuscript
2026-09-26 to 2027-03-31; In progress.
Expected outcome: Update methods, figures, claims, citations and open questions as research changes. Writing begins with Stage 1 and continues through review, new experiments and later consolidation.
Prerequisites: None specified.
CAP6942 | Course deliverables
33. Bibliography, canvas and project-plan submissions
2026-09-26 to 2026-09-27; In progress.
Expected outcome: Submit the annotated bibliography and Research Canvas for Team Assignment 1, and the research project plan for Team Assignment 2. Both are due September 27 at 23:59 Eastern.
Prerequisites: None specified.
34. Prepare final report, presentation and video
2026-11-16 to 2026-12-06; Planned.
Expected outcome: Adapt the evolving manuscript and evidence to the course report, presentation and video requirements. Rehearse explanations and incorporate teammate and advisor feedback.
Prerequisites: None specified.
35. Course rehearsal checkpoint
2026-12-01 to 2026-12-01; Planned.
Expected outcome: Rehearse the scientific account and record corrections; confirm the course’s exact instructions in WebCourses.
Prerequisites: None specified.
36. Final course report checkpoint
2026-12-07 to 2026-12-07; Planned.
Expected outcome: Review evidence, attribution and AI disclosure; confirm and complete the required course submission.
Prerequisites: 34, 35.
37. Course presentation and video checkpoint
2026-12-08 to 2026-12-08; Planned.
Expected outcome: Deliver the course presentation/video using the reviewed evidence and acknowledged limitations.
Prerequisites: 34, 35.
Research continuation | Provisional January–March 2027
38. Further experiments and external validation
2027-01-04 to 2027-02-28; Conditional.
Expected outcome: Select and run extensions justified by the reviewed evidence, biological relevance, collaborators and available resources.
Prerequisites: 29.
39. Consolidate manuscript and review publication readiness
2027-02-01 to 2027-03-31; Planned.
Expected outcome: Refine the manuscript already underway, integrate additional evidence and seek group feedback. Venue, submission date and final research end remain undecided.
Prerequisites: None specified.
40. March research review and next-step decision
2027-03-31 to 2027-03-31; Planned.
Expected outcome: Review the evidence and decide whether to extend the experiments, revise the manuscript, prepare a submission or change direction. Adjust the timeline to the chosen next steps.
Prerequisites: 39.
Sources: Fall 2026 CAP6942 Schedule.pdf; project README.md; team meeting and schedule corrections supplied September 26, 2026.

## Slide 2
Stage 1 | Understanding, Reproducibility and Alignment
Initial core reading completed September 21. Discussion, data work, early implementation and writing now overlap.
Task / research outcome
Status
Dates
9/21
9/28
10/5
Study and interpretation
2. Paper discussion and notebook walkthrough
In progress
9/21–10/5
6. Interpret representation metrics and pilot results
In progress
9/21–10/4
7. Draft a measurable definition of alignment
In progress
9/21–10/4
Data and reproducibility
3. Data labels, sequence regions and duplicates
In progress
9/21–10/4
4. Train/test separation and preprocessing
In progress
9/21–10/4
5. Run history, seeds and reproducibility
In progress
9/21–10/4
Early implementation, writing and collaboration
8. Map BioLangFusion/IsoFormer inputs incl. DNA
Planned
9/28–9/30
9. Implement and check the BioLangFusion pilot
Planned
10/1–10/4
10. Write Stage 1 methods and findings in Overleaf
In progress
9/26–10/4
11. Clarify the lab tokenizer and benchmark opportunity
Planned
9/28–10/5
October 5 review and follow-up
12. Prepare evidence and questions for Mina
Planned
10/1–10/4
13. Review with Mina and working alignment definition
Planned
10/5
14. Revise Stage 1 claims, figures and methods
Planned
10/6–10/11
15. Specify the next matched comparison
Planned
10/6–10/11
Complete
In progress
Planned
Conditional
Milestone / deadline
As of Sep 29, 2026
October 5 milestone: agree what alignment means for this study, how to measure it, and the next controlled comparison.
The following week is reserved for feedback and corrections. Continued study informs the experiments and manuscript.
2
Notes: Stage 1 | Understanding, Reproducibility and Alignment
The initial six-paper review was completed by September 21. Continued discussion and scientific interpretation remain active.
Dates beyond current work are planning windows. September 21 start dates for ongoing tasks are approximate anchors, not reconstructed activity logs.
October 5 is the next planned Mina meeting. The Stage 1 milestone is a working definition of alignment and a decision about the next matched comparison. Specify the objects being aligned, biological question, unit, metric and reference, and what the result can support.
Stage 1 includes early fusion prototyping to develop understanding. Stage 2 is the proposed structured comparison programme following the review. Feedback may change its scope and timing.
The Coupled Mamba priority follows the project README and the September 23 meeting. Optional comparisons are candidates, and the team will select a feasible subset.
Research coordination began September 14. Stage 1 manuscript drafting is underway in Overleaf and continues as methods and findings change.
The September 27 deadline covers the bibliography and Research Canvas assignment and the research project plan assignment. December 1, 7 and 8 course dates follow the Fall 2026 CAP6942 schedule; WebCourses controls any changes.
January–March is a provisional continuation window. The research end and publication submission date have not been set.
The lab tokenizer and collaborating group still need to be identified. Clarifying the opportunity precedes committing to a benchmark.
AI supports literature study, implementation, analysis and writing. Source checking, experiment interpretation and research decisions are included in each relevant work package.
AI assistance: OpenAI Codex assisted with organizing and wording this research plan. Dates and task descriptions were compared with the course schedule, project README and team meeting notes.
Study and interpretation
2. Continue paper synthesis and notebook walkthrough
2026-09-21 to 2026-10-05; In progress.
Expected outcome: Explain biological inputs, frozen encoders, pooling, probes and metrics; connect each retained result to the relevant paper and its limitations.
Prerequisites: None specified.
6. Interpret representation metrics and pilot findings
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Explain what CKA, neighborhood, CCA/retrieval and predictive probes measure; distinguish observations from explanations. Prepare PCA/variance and layer-choice questions for Mina.
Prerequisites: None specified.
7. Draft an operational definition of alignment
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Define objects being related, biological correspondence versus representation similarity, sample/position unit, metric, reference or null, and permitted conclusions. Keep useful fusion as a separate test.
Prerequisites: None specified.
Data and reproducibility
3. Check label meaning, sequence regions and duplicates
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Record assay/target provenance, retained rows, sequence regions, duplicates and translation assumptions before drawing biological conclusions.
Prerequisites: None specified.
4. Check train/test separation and preprocessing
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Identify evaluation unit; check whether duplicate or related sequences cross train/test boundaries and whether fitted preprocessing uses training data only. Document what the split can support.
Prerequisites: None specified.
5. Trace runs, seeds and reproducibility evidence
2026-09-21 to 2026-10-04; In progress.
Expected outcome: Link selected outputs to notebook, data, model revisions, environment, split and seed settings. Compare reruns and investigate differences in results.
Prerequisites: None specified.
Early implementation, writing and collaboration
8. Map BioLangFusion methods to our inputs
2026-09-28 to 2026-09-30; Planned.
Expected outcome: Compare paper and local checkpoints, tokenization, sequence regions, codon mapping, pooling, labels, splits and metrics. Document the changes needed to adapt the method to our inputs.
Prerequisites: None specified.
9. Build and check a BioLangFusion methods pilot
2026-10-01 to 2026-10-04; Planned.
Expected outcome: Test input/feature correspondence and selected simple fusion methods in a small prototype. Compare outputs with controls and bring feasibility findings and deviations from the paper to the October 5 review.
Prerequisites: 8.
10. Draft Stage 1 methods and findings in Overleaf
2026-09-26 to 2026-10-04; In progress.
Expected outcome: Join Mina’s project, draft Stage 1 background/methods, attach supported figures and annotate unresolved claims. This is the first writing increment of the living manuscript.
Prerequisites: None specified.
11. Clarify the lab tokenizer and benchmark opportunity
2026-09-28 to 2026-10-05; Planned.
Expected outcome: Ask Julian for the exact group, tokenizer/paper and intended benchmark task. Establish inputs, access, comparison unit and collaborators before promising a shared experiment.
Prerequisites: None specified.
October 5 review and follow-up
12. Prepare the Oct 5 evidence and question set
2026-10-01 to 2026-10-04; Planned.
Expected outcome: Assemble the explainable pipeline, source-linked findings, unresolved results, BioLangFusion pilot status and alignment-definition proposal. Distinguish established evidence from open hypotheses.
Prerequisites: None specified.
13. Oct 5 review and working alignment definition
2026-10-05 to 2026-10-05; Planned.
Expected outcome: Review evidence with Mina and agree a working definition of alignment, its measurements and limits, and the next comparison. Record remaining questions and required revisions.
Prerequisites: 2, 3, 4, 5, 6, 7, 9, 10, 12.
14. Revise Stage 1 claims, figures and methods
2026-10-06 to 2026-10-11; Planned.
Expected outcome: Incorporate Mina’s feedback in the notebook explanations and manuscript; correct unsupported interpretations and identify specific reruns or experiments needed.
Prerequisites: 13.
15. Specify the first matched comparison protocol
2026-10-06 to 2026-10-11; Planned.
Expected outcome: Set biological question, target, evaluation unit, data exclusions, checkpoints, preprocessing, metrics, seeds, tuning budget and success/stop criteria. Architecture priority remains Coupled Mamba; details follow the review.
Prerequisites: 13.
Sources: Fall 2026 CAP6942 Schedule.pdf; project README.md; team meeting and schedule corrections supplied September 26, 2026.

## Slide 3
Stage 2 | Experiments, Interpretation and Revision
Proposed comparison schedule after the October 5 review. Select optional experiments as the findings develop.
Task / research outcome
Status
Dates
10/5
10/12
10/19
10/26
11/2
11/9
11/16
11/23
Core comparison sequence
16. Prepare single-model and simple-fusion baselines
Planned
10/6–10/11
17. Run matched BioLangFusion-style comparisons
Planned
10/12–10/18
18. Run diagnostic and control comparisons
Planned
10/12–10/18
19. Interpret baselines and revise the next experiment
Planned
10/19–10/25
20. Prepare Coupled Mamba inputs and feasibility tests
Planned
10/12–10/25
21. Compare Coupled Mamba with matched baselines
Planned
10/26–11/8
Repeated runs, interpretation and revision
28. Repeat runs, quantify uncertainty and revise claims
Planned
10/12–11/22
29. Synthesize findings, limitations and next steps
Planned
11/16–11/29
Optional comparisons | Subject to scope and feasibility
22. Layer depth and PCA/variance comparisons
Conditional
10/19–11/1
23. Alignment-objective ablation
Conditional
11/2–11/8
24. More DNA, RNA and protein encoders
Conditional
11/9–11/15
25. IsoFormer-style fusion comparison
Conditional
11/9–11/15
26. Agree tokenizer benchmark scope and protocol
Conditional
10/6–10/18
27. Lab-tokenizer benchmark pilot
Conditional
11/2–11/15
Complete
In progress
Planned
Conditional
Milestone / deadline
As of Sep 29, 2026
Each comparison includes implementation, controlled runs, interpretation, revision and an update to the manuscript.
AI assistance: OpenAI Codex helped organize this plan; Claude assisted with the DNA-scope revision. Dates and task descriptions were checked against course materials and project notes.
3
Notes: Stage 2 | Experiments, Interpretation and Revision
The initial six-paper review was completed by September 21. Continued discussion and scientific interpretation remain active.
Dates beyond current work are planning windows. September 21 start dates for ongoing tasks are approximate anchors, not reconstructed activity logs.
October 5 is the next planned Mina meeting. The Stage 1 milestone is a working definition of alignment and a decision about the next matched comparison. Specify the objects being aligned, biological question, unit, metric and reference, and what the result can support.
Stage 1 includes early fusion prototyping to develop understanding. Stage 2 is the proposed structured comparison programme following the review. Feedback may change its scope and timing.
The Coupled Mamba priority follows the project README and the September 23 meeting. Optional comparisons are candidates, and the team will select a feasible subset.
Research coordination began September 14. Stage 1 manuscript drafting is underway in Overleaf and continues as methods and findings change.
The September 27 deadline covers the bibliography and Research Canvas assignment and the research project plan assignment. December 1, 7 and 8 course dates follow the Fall 2026 CAP6942 schedule; WebCourses controls any changes.
January–March is a provisional continuation window. The research end and publication submission date have not been set.
The lab tokenizer and collaborating group still need to be identified. Clarifying the opportunity precedes committing to a benchmark.
AI supports literature study, implementation, analysis and writing. Source checking, experiment interpretation and research decisions are included in each relevant work package.
AI assistance: OpenAI Codex assisted with organizing and wording this research plan. Dates and task descriptions were compared with the course schedule, project README and team meeting notes.
Core comparison sequence
16. Harden single-model and simple-fusion baselines
2026-10-06 to 2026-10-11; Planned.
Expected outcome: Prepare comparable single-encoder and concatenation + MLP predictors, input tests and controlled configurations. Keep the original linear concatenation probe distinct. Final comparisons use protocol 15.
Prerequisites: 13.
17. Run matched BioLangFusion-style comparisons
2026-10-12 to 2026-10-18; Planned.
Expected outcome: Compare selected paper-inspired fusion methods and unimodal baselines on the same evaluation data, with adaptations and resources reported. Preserve null or negative results.
Prerequisites: 9, 15, 16.
18. Repeat diagnostics and null/control comparisons
2026-10-12 to 2026-10-18; Planned.
Expected outcome: Check label/feature controls, synonymous-input behavior and representation diagnostics under the agreed evaluation. Test whether the claimed signal survives the relevant nulls.
Prerequisites: 14, 15, 16.
19. Interpret baseline findings and revise the next experiment
2026-10-19 to 2026-10-25; Planned.
Expected outcome: Compare effect sizes, variation and failure cases; distinguish geometry from predictive complementarity. Revise the question and manuscript before choosing additional complexity.
Prerequisites: 17, 18.
20. Prepare Coupled Mamba inputs and feasibility tests
2026-10-12 to 2026-10-25; Planned.
Expected outcome: Implement the prioritized architecture with explicit sequence/feature correspondence; test dimensions, controlled cases and resource feasibility while baseline analysis proceeds.
Prerequisites: 15, 16.
21. Evaluate Coupled Mamba against matched baselines
2026-10-26 to 2026-11-08; Planned.
Expected outcome: Compare predictive performance, uncertainty, runtime and memory under the matched evaluation protocol. Interpret gains, losses or unchanged performance against the baseline.
Prerequisites: 19, 20.
Repeated runs, interpretation and revision
28. Repeat runs, estimate uncertainty and revise interpretations
2026-10-12 to 2026-11-22; Planned.
Expected outcome: Repeat selected configurations as results arrive; investigate variation, leakage or contradictory findings, and revise claims. This spans the experiment cycle rather than following implementation as a single final check.
Prerequisites: 15, 16.
29. Synthesize evidence, limitations and next decisions
2026-11-16 to 2026-11-29; Planned.
Expected outcome: Build a comparison table with sources/runs, uncertainty, resource costs, negative findings and scope limits. Review which conclusions are supported and which further experiments are justified.
Prerequisites: 19, 21.
Optional comparisons | Subject to scope and feasibility
22. Candidate layer and PCA/variance comparisons
2026-10-19 to 2026-11-01; Conditional.
Expected outcome: After choosing the relevant encoder/layer question, compare selected representations or variance subspaces. Fit any reduction within training data and separate using an earlier layer from truncating or retraining a model.
Prerequisites: 18.
23. Candidate alignment-objective ablation
2026-11-02 to 2026-11-08; Conditional.
Expected outcome: If selected, compare the same fusion setup with and without the specified alignment objective under matched tuning. The pilot’s alignment/error association is not evidence that the loss must help or hurt.
Prerequisites: 19, 20.
24. Candidate additional RNA-encoder comparisons
2026-11-09 to 2026-11-15; Conditional.
Expected outcome: If selected, compare individual checkpoints and combinations while controlling downstream capacity, input coverage and tuning. Different pretraining corpora alone do not establish complementarity.
Prerequisites: 19.
25. Candidate IsoFormer-style fusion comparison
2026-11-09 to 2026-11-15; Conditional.
Expected outcome: Evaluate the second-priority cross-attention candidate only if the reviewed research question and resource budget justify it. Report relevant differences from IsoFormer’s fine-tuning regime.
Prerequisites: 21.
26. Agree tokenizer benchmark feasibility and protocol
2026-10-06 to 2026-10-18; Conditional.
Expected outcome: With the identified lab group, agree a shared task, data, tokenizer version, access and fair comparison protocol.
Prerequisites: 11, 13.
27. Candidate lab-tokenizer benchmark pilot
2026-11-02 to 2026-11-15; Conditional.
Expected outcome: Run only after collaborators agree scope and access and a matched protocol exists. Keep tokenizer effects separate from model capacity, training data and downstream evaluation differences.
Prerequisites: 26.
Sources: Fall 2026 CAP6942 Schedule.pdf; project README.md; team meeting and schedule corrections supplied September 26, 2026.