## Gantt
Research Project Plan: Aligning and Fusing Frozen RNA and Protein Foundation Models
Julian McKinley ¦ MSDA Capstone, UCF ¦ Advisor: Mina Basirat, PhD ¦ Weekly through Dec 2026, monthly after
How to use: edit Status, Start, End, Depends on, and Owner (columns C to H). Bars and milestone markers (◆ = start date equals end date) redraw automatically. Bar shading: dark = Done, amber = In progress, light gray = Planned. The current week is highlighted in the date header.
[8 empty] | Fall 2026 (weekly, week starting) | [14 empty] | 2027 (monthly)
ID | Task | Status | Start | End | Days | Depends on | Owner | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Setup and Literature
1 | Lab onboarding and advisor meetings (Garibay lab, Mina) | Done | 2026-08-31 | 2026-09-13 | 14
2 | Literature review: 6 core papers and written reviews | Done | 2026-09-07 | 2026-09-20 | 14 | 1
3 | Annotated bibliography and research canvas | In progress | 2026-09-21 | 2026-09-27 | 7 | 2
4 | Capstone planning docs (Statement of Work, Requirements, Project Plan) | In progress | 2026-09-21 | 2026-10-04 | 14 | 2
Stage 1: Representation Analysis
5 | Data prep: CodonBERT datasets, frame and start-codon checks | Done | 2026-09-14 | 2026-09-20 | 7
6 | Pilot analysis (1,000 seqs): probes, CKA, CCA, retrieval, mRFP control | In progress | 2026-09-14 | 2026-09-27 | 14 | 5
7 | Progress meeting with Mina (1-2 slides) | Planned | 2026-09-23 | 2026-09-23 | 1 | 6 |  |  |  |  | ◆
8 | Scale Stage 1 to full ~41K mRNA Stability set and mRFP Expression labels | Planned | 2026-09-28 | 2026-10-11 | 14 | 6
9 | Interpretability follow-ups (attention vs. motifs, species subgroup check) | Planned | 2026-10-05 | 2026-10-18 | 14 | 8
10 | Milestone: Stage 1 findings reviewed with Mina | Planned | 2026-10-16 | 2026-10-16 | 1 | 8, 9 | [7 empty] | ◆
Stage 2: Fusion and Benchmarking
11 | Codon-level alignment module (resample RNA and protein embeddings) | Planned | 2026-10-12 | 2026-10-25 | 14 | 10
12 | Baselines: single-modality and concatenation models | Planned | 2026-10-19 | 2026-11-01 | 14 | 11
13 | Cross-attention fusion model | Planned | 2026-10-26 | 2026-11-08 | 14 | 11
14 | Coupled Mamba fusion model | Planned | 2026-11-02 | 2026-11-15 | 14 | 11
15 | Alignment-loss ablation (with vs. without explicit alignment) | Planned | 2026-11-09 | 2026-11-22 | 14 | 13, 14
16 | Benchmark and statistics (5-fold CV, R-squared, Spearman) | Planned | 2026-11-16 | 2026-11-29 | 14 | 12, 13, 14, 15
17 | Agentic AI component (capstone requirement) | Planned | 2026-10-12 | 2026-11-22 | 42 | 4
Capstone Deliverables
18 | Weekly meetings with Mina and teammate | In progress | 2026-09-21 | 2026-12-06 | 77
19 | Final report writing | Planned | 2026-11-16 | 2026-12-06 | 21 | 16
20 | Final presentation and GitHub documentation | Planned | 2026-11-30 | 2026-12-06 | 7 | 16
21 | Milestone: Final capstone submission | Planned | 2026-12-11 | 2026-12-11 | 1 | 19, 20 | [15 empty] | ◆
After Capstone: Toward Publication
22 | Extended experiments (full benchmark suite, more encoders) | Planned | 2027-01-04 | 2027-02-28 | 56 | 21
23 | Manuscript drafting with Mina | Planned | 2027-02-01 | 2027-03-31 | 59 | 22
24 | Milestone: Paper submission (target venue TBD with Mina) | Planned | 2027-04-15 | 2027-04-15 | 1 | 23 | [19 empty] | ◆
25 | Revisions and public code release | Planned | 2027-04-16 | 2027-05-31 | 46 | 24

## Notes
Assumptions behind this plan
Semester end: final capstone deliverables assumed due the week of Dec 7, 2026 (Julian: early December).
Work continues after the capstone toward publication (Julian); 2027 dates are targets to confirm with Mina.
Stage 1 status reflects Code/Stage1.ipynb as of Sep 22, 2026 (1,000-sequence pilot complete).
Agentic AI component: required by the capstone course; scope and dates to confirm with the course professor.
Owner column is left blank for Julian to assign tasks between himself and Chase.
Timeline headers: weekly columns show the Monday each week starts; monthly columns show the first of the month.