## Slide 1
Research Project Plan (Gantt): Aligning and Fusing Frozen RNA and Protein Foundation Models
Julian McKinley | MSDA Capstone, UCF | Advisor: Mina Basirat, PhD | Weekly through the Fall 2026 capstone, monthly afterward toward publication
Fall 2026 capstone (weekly, week starting)
2027 (monthly)
Task
Status
8/31
9/7
9/14
9/21
9/28
10/5
10/12
10/19
10/26
11/2
11/9
11/16
11/23
11/30
12/7
Jan
Feb
Mar
Apr
May
Setup and Literature
1. Lab onboarding and advisor meetings (Garibay lab, Mina)
Done
2. Literature review: 6 core papers and written reviews
Done
3. Annotated bibliography and research canvas
In progress
4. Capstone planning docs (Statement of Work, Requirements, Project Plan)
In progress
Stage 1: Representation Analysis
5. Data prep: CodonBERT datasets, frame and start-codon checks
Done
6. Pilot analysis (1,000 seqs): probes, CKA, CCA, retrieval, mRFP control
Done
7. Progress meeting with Mina (Stage 1 results)
Planned
Sep 23
8. Scale Stage 1 to full ~41K mRNA Stability set and mRFP Expression labels
Planned
9. Interpretability follow-ups (species subgroup check, other attention layers and heads)
Planned
10. Milestone: Stage 1 findings reviewed with Mina
Planned
Oct 16
Stages 2 to 4: Alignment, Fusion, and Benchmarking
11. Stage 2: codon-grid alignment (resample RNA onto the protein codon grid)
Planned
12. Stage 3: baselines (single-modality, concatenation + MLP)
Planned
13. Stage 3: cross-attention fusion model
Planned
14. Stage 3: Coupled Mamba fusion model
Planned
15. Stage 3: alignment-loss ablation (with vs. without explicit alignment)
Planned
16. Stage 4: benchmark and statistics (5-fold CV, R-squared, Spearman)
Planned
17. Agentic AI component (capstone requirement)
Planned
Capstone Deliverables
18. Weekly meetings with Mina and teammate
In progress
19. Final report writing
Planned
20. Final presentation and GitHub documentation
Planned
21. Milestone: Final capstone submission
Planned
Dec 11
After Capstone: Toward Publication
22. Extended experiments (full benchmark suite, more encoders)
Planned
23. Manuscript drafting with Mina
Planned
24. Milestone: Paper submission (target venue TBD with Mina)
Planned
Apr 15
25. Revisions and public code release
Planned
Done
In progress
Planned
Milestone
Today (Sep 23, 2026)
Agentic AI scope and 2027 dates to be confirmed with the course professor and Mina.